## CONFIG
IBM Cybersecurity Services — Quantum Safe Transformation | [6 empty] | HOW TO USE THIS SHEET (CONFIG)
CELL TYPE GUIDE: | [6 empty] | PURPOSE: | Central configuration sheet. Contains IBM-standard rates, delivery parameters, maturity assessment, and learning curve definitions. All other sheets pull values from here.
IBM Standard — do not modify | [6 empty] | WHO FILLS THIS IN: | IBM pre-populates steel-blue cells with standard rates. The ITSO adjusts cream-colored cells to reflect the client's delivery model and organizational maturity.
Client Input — please fill in | [6 empty] | DATA FLOW: | CONFIG feeds UNITS (blended rates per unit type, risk %, CG&E %, maturity multiplier, learning curve) and TIMELINE (CG&E %, maturity multiplier)
Calculated — auto-computed
RATE CARD | [6 empty] | SECTION: RATE CARD | Hourly/monthly rates for 5 role tiers, split by delivery location (onshore vs offshore). Blended rate is auto-calculated.
Role Tier | Onshore Rate (USD/mo) | Offshore Rate (USD/mo) | Onshore % | Offshore % | Blended Role Rate (USD/mo) |  | Row | Explanation
Architect / SME | 28000 | 12000 | 40% | 60% |  |  | Architect / SME | Senior cryptography experts, solution architects. Highest rate. Used heavily in Discovery, Design, and CMU/PKI work.
Senior Engineer | 24000 | 10000 | 35% | 65% |  |  | Senior Engineer | Experienced developers who lead implementation. Core of most unit types.
Developer | 20000 | 8000 | 30% | 70% |  |  | Developer | Mid-level developers doing bulk implementation. Dominant role in AMU and DMU.
Tester / QA | 18000 | 7000 | 25% | 75% |  |  | Tester / QA | Security testers, pen testers, regression test engineers. Key in Phase 4.
Project Manager | 26000 | 11000 | 40% | 60% |  |  | Project Manager | Engagement/delivery managers. Higher proportion in governance-heavy units (FAU, VTU).
[7 empty] | FORMULA: | Blended Role Rate = (Onshore Rate x Onshore %) + (Offshore Rate x Offshore %) Example: Architect = ($28,000 x 40%) + ($12,000 x 60%) = $18,400/mo
BLENDED RATE BY UNIT TYPE | [6 empty] | SECTION: BLENDED RATE BY UNIT | Each unit type has a different role mix. FAU is governance-heavy (more PM, Architect). AMU is implementation-heavy (more Developers). The blended unit rate = role mix x role rates.
Unit Type | Architect % | Sr Engineer % | Developer % | Tester % | PM % | Blended Unit Rate (USD/mo) | Row | Explanation
FAU | 20% | 30% | 20% | 10% | 20% |  | FAU | Governance-focused: 20% Arch, 30% Sr, 20% Dev, 10% Test, 20% PM. High PM/Arch mix for cross-unit coordination.
NMU | 15% | 25% | 35% | 15% | 10% |  | NMU | Network/infra: 15% Arch, 25% Sr, 35% Dev, 15% Test, 10% PM. Developer-heavy for config automation.
AMU | 10% | 20% | 40% | 20% | 10% |  | AMU | Largest unit (8000 apps): 10% Arch, 20% Sr, 40% Dev, 20% Test, 10% PM. Factory model.
PMU | 15% | 25% | 30% | 20% | 10% |  | PMU | Platform/cloud: 15% Arch, 25% Sr, 30% Dev, 20% Test, 10% PM.
CMU | 20% | 30% | 25% | 10% | 15% |  | CMU | Specialist-heavy: 20% Arch, 30% Sr, 25% Dev, 10% Test, 15% PM. Highest architect mix for PKI complexity.
DMU | 10% | 20% | 40% | 20% | 10% |  | DMU | Data migration: Same as AMU mix.
DAU | 10% | 25% | 40% | 15% | 10% |  | DAU | Pipeline/tooling: 10% Arch, 25% Sr, 40% Dev, 15% Test, 10% PM.
VTU | 5% | 15% | 15% | 5% | 60% |  | VTU | Vendor management: 5% Arch, 15% Sr, 15% Dev, 5% Test, 60% PM. Highest PM mix for coordination work.
[7 empty] | FORMULA: | Blended Unit Rate = (Arch% x Arch Rate) + (Sr% x Sr Rate) + (Dev% x Dev Rate) + (Test% x Test Rate) + (PM% x PM Rate)
GLOBAL PARAMETERS | [6 empty] | SECTION: GLOBAL PARAMETERS | Program-wide settings that affect all cost calculations.
Working Days per Month | 20 | [5 empty] | Working Days/Month | Standard = 20. Used for converting FTE-months to mandays if needed.
Risk Contingency % | 20% | [5 empty] | Risk Contingency % | Default 20%. Applied to each unit's subtotal. Industry standard 15-25% for ROM-stage estimates.
CG&E (Central Governance & Enablement) % | 10% | [5 empty] | CG&E % | Default 10%. Covers: PMO, governance board, enterprise architecture oversight, compliance, training.
MATURITY ASSESSMENT (PQC Readiness) | [6 empty] | SECTION: MATURITY ASSESSMENT | Based on PKI Consortium PQC Maturity Model (PQCMM). Lower maturity = higher cost.
Dimension | Score (1-5) | Guidance |  |  |  |  | How to score: | Score each dimension 1-5 based on current client state. Be honest — overestimating maturity leads to underestimating costs.
Cryptographic Inventory & Visibility | 3 | 1=None, 3=Partial CMDB, 5=Full CBOM |  |  |  |  | Crypto Inventory | Does the client know what crypto they use? 1=No inventory. 3=Partial CMDB. 5=Full CBOM with automated discovery.
Governance & Policy Maturity | 3 | 1=Ad-hoc, 3=Defined policies, 5=Enforced & audited |  |  |  |  | Governance & Policy | Are there crypto policies? 1=Ad-hoc. 3=Written policies, some enforcement. 5=Policies enforced via automation.
Automation & Tooling Readiness | 2 | 1=Manual, 3=Some automation, 5=Full CI/CD crypto checks |  |  |  |  | Automation & Tooling | How automated is crypto management? 1=Manual. 3=Some automation. 5=Full CI/CD with crypto checks.
Skills & Organizational Readiness | 3 | 1=No PQC awareness, 3=Some training, 5=Dedicated team |  |  |  |  | Skills & Readiness | Does the org understand PQC? 1=No awareness. 3=Some training. 5=Dedicated PQC team, funded program.
Architecture Modernization | 2 | 1=Monolith/legacy, 3=Mixed, 5=Cloud-native/modular |  |  |  |  | Architecture | How modern is the stack? 1=Monoliths/mainframes. 3=Mixed. 5=Cloud-native, microservices, modular.
Average Maturity Score | [6 empty] | Average Score | Simple average of the 5 dimension scores.
Maturity Multiplier |  | 1.25=Immature, 1.0=Moderate, 0.85=Excellent |  |  |  |  | Maturity Multiplier | Maps average to cost multiplier: 1.0-1.5 = 1.25x (25% uplift) 1.6-2.5 = 1.15x (15% uplift) 2.6-3.5 = 1.00x (baseline) 3.6-4.5 = 0.90x (10% discount) 4.6-5.0 = 0.85x (15% discount)
LEARNING CURVE (AMU) | [6 empty] | SECTION: LEARNING CURVE (AMU) | Based on Wright's Law. As more apps are migrated, per-app cost drops from reuse, automation, and institutional knowledge.
Wave | App Range | Cost Multiplier |  |  |  |  | How it works: | 8000 apps are migrated in waves. Each wave gets a cost multiplier. The blended average determines effective per-app cost reduction.
Pathfinder | 1 - 50 | 1.5 |  |  |  |  | Wave 1: Pathfinder (1-50) | 1.5x. First 50 apps are expensive: building tooling, playbooks, training teams.
Early | 51 - 200 | 1 |  |  |  |  | Wave 2: Early (51-200) | 1.0x (baseline). Team is ramped, basic patterns exist.
Factory | 201 - 1,000 | 0.65 |  |  |  |  | Wave 3: Factory (201-1000) | 0.65x. Automation operational, templates for common patterns.
Mature | 1,001 - 4,000 | 0.45 |  |  |  |  | Wave 4: Mature (1001-4000) | 0.45x. Maximum automation, junior staff execute from runbooks.
Late | 4,001+ | 0.3 |  |  |  |  | Wave 5: Late (4001+) | 0.30x. Near-full automation. Only edge cases need human attention.
WORKED EXAMPLE: Blended Learning Curve Factor
[7 empty] | Given: 8,000 total apps | Wave 1: min(50, 8000) = 50 apps x 1.50 = 75.0 Wave 2: min(150, 8000-50) = 150 apps x 1.00 = 150.0 Wave 3: min(800, 8000-200) = 800 apps x 0.65 = 520.0 Wave 4: min(3000, 8000-1000) = 3000 apps x 0.45 = 1,350.0 Wave 5: max(0, 8000-4000) = 4000 apps x 0.30 = 1,200.0
[7 empty] | Blended Factor: | (75 + 150 + 520 + 1350 + 1200) / 8000 = 3,295 / 8,000 = 0.4119 Average app costs 41.19% of baseline — a 59% reduction.

## INPUT
IBM Cybersecurity Services — Client Environment Profile | [6 empty] | STEP-BY-STEP GUIDE
CELL TYPE GUIDE: | [6 empty] | PURPOSE: Your inputs here drive ALL cost calculations across the workbook.
IBM Standard — do not modify | [6 empty] | STEPS: 1. Enter Client Name and Engagement ID 2. Score each Complexity Factor (1-3) 3. Enter Unit Counts from your discovery 4. Distribute total applications across archetypes 5. Verify the archetype total matches (Validation = 'OK')
Client Input — please fill in
Calculated — auto-computed
BASE INFORMATION
Client Name
Engagement ID
COMPLEXITY ASSESSMENT | [6 empty] | SECTION: COMPLEXITY ASSESSMENT
Factor | Score (1-3) | 1 = Low | 2 = Medium | 3 = High | Weight | Weighted Score | Each factor scored 1 (Low), 2 (Medium), 3 (High). Multiplied by Weight to produce Weighted Score. Composite multiplier ranges 1.0x to 2.0x.
Crypto Usage | 1 | TLS only, libraries abstracted | Mix of TLS + embedded, some custom | Deep custom crypto, HSM, PKI-embedded | 25% |  | Crypto Usage: How deeply is cryptography embedded? TLS only via libraries = 1. Custom encryption + HSM integrations = 3.
Dependencies | 1 | Self-contained, few integrations | 5-15 dependent systems | 15+ systems, cross-org | 20% |  | Dependencies: How many external systems connect? Self-contained = 1. 15+ systems with cross-org flows = 3.
Architecture Type | 1 | Cloud-native, modular | Mixed modern/legacy | Monolith, mainframe, tightly coupled | 25% |  | Architecture: Cloud-native microservices = 1. Mixed = 2. Monolithic mainframe = 3.
Change Readiness | 1 | CI/CD, automated tests | Semi-automated, manual gates | Manual deployment, limited tests | 15% |  | Change Readiness: Full CI/CD = 1. Semi-automated = 2. Manual deployment = 3.
Urgency | 1 | Planned, flexible timeline | Regulatory deadline within 2 years | Immediate, compliance-critical | 15% |  | Urgency: Flexible timeline = 1. Regulatory deadline in 2 years = 2. Immediate compliance = 3.
Composite Complexity Multiplier | [6 empty] | FORMULA: Multiplier = 0.5 + (Sum of Weighted Scores) x 0.5 All Low: 1.00 x 0.5 + 0.5 = 1.0x All High: 3.00 x 0.5 + 0.5 = 2.0x
(Range: 1.0x at all-Low to 2.0x at all-High)
UNIT COUNT QUESTIONS | [6 empty] | SECTION: UNIT COUNT QUESTIONS
Question | Count | [5 empty] | These counts drive unit sizing on the UNITS sheet. Each question maps to one of 8 unit types:
Number of independently governed delivery units (BUs, entities, geos) with own dev/release authority | 22 | [5 empty] | Maps to FAU. Count BUs, legal entities, or regions that independently manage crypto policies.
Number of distinct network trust domains or connectivity zones | 10 | [5 empty] | Maps to NMU. Count distinct network zones or trust domains with independent TLS/IPsec/VPN.
Total number of applications (all types) | 8000 | [5 empty] | Maps to AMU. Total app count — the single biggest cost driver. Include all apps using any cryptography.
Number of distinct runtime platforms (cloud accounts, on-prem, containers, mainframe) | 20 | [5 empty] | Maps to PMU. Count runtime platforms: cloud subscriptions, on-prem clusters, container platforms, LPARs.
Number of PKI/KMS domains that need to be transformed | 20 | [5 empty] | Maps to CMU. Count PKI hierarchies and KMS instances needing quantum-safe migration.
Number of data store classes requiring cryptographic control | 80 | [5 empty] | Maps to DMU. Count data store classes by encryption type: databases, object stores, backup, archival.
Number of CI/CD pipelines or deployment paths handling crypto material | 10 | [5 empty] | Maps to DAU. Count CI/CD pipelines that create, rotate, or validate cryptographic material.
Number of vendor/SaaS products where crypto is externally controlled | 250 | [5 empty] | Maps to VTU. Count vendor products where crypto is externally controlled (SaaS, contracted services).
APPLICATION ARCHETYPE DISTRIBUTION | [6 empty] | SECTION: ARCHETYPE DISTRIBUTION
Archetype | Count | % of Total |  |  |  |  | Break down total apps into 6 categories. This determines weighted average effort per app on ESTIMATE sheet.
Simple Web App / API Service | 3200 | [5 empty] | Simple Web App (0.9 FTE-mo): Standard TLS. Minimal crypto surface. Easiest to migrate.
Mainframe / Legacy System | 800 | [5 empty] | Mainframe (4.0 FTE-mo): COBOL/JCL with embedded crypto. Specialist skills required. Most expensive per app.
ERP / Packaged Application | 600 | [5 empty] | ERP / Packaged (3.0 FTE-mo): SAP, Oracle. Effort is in vendor coordination + config.
Mobile Application | 400 | [5 empty] | Mobile (1.0 FTE-mo): iOS/Android. Mostly TLS + cert pinning. Moderate effort.
Microservice / Cloud-Native | 2200 | [5 empty] | Microservice (0.6 FTE-mo): Cloud-native, containerized. Cheapest to migrate.
Monolith / Legacy Custom | 800 | [5 empty] | Monolith (3.5 FTE-mo): Large custom apps with hardcoded crypto. High effort.
Total | [6 empty] | Counts MUST sum to total applications. Check Validation row.
Validation

## ESTIMATE
IBM Cybersecurity Services — Per-Application Effort Estimator | [6 empty] | HOW THIS SHEET WORKS
PURPOSE: Calculates weighted average effort per application, considering archetype mix and complexity. Output (cell E32) feeds AMU on UNITS sheet.
PHASE EFFORT DISTRIBUTION | [6 empty] | DATA FLOW: Receives: Complexity Multiplier from INPUT!G17, Archetype counts from INPUT!B33:B38 Produces: Weighted Average Effort (E32) for UNITS sheet
Phase | 1: Discovery (15%) | 2: Design (10%) | 3: Development (45%) | 4: Testing (20%) | 5: Deployment (10%) | Total
BASE EFFORT BY ARCHETYPE (FTE-months per app, before complexity) | [6 empty] | SECTION: BASE EFFORT BY ARCHETYPE
Archetype | 1: Discovery (15%) | 2: Design (10%) | 3: Development (45%) | 4: Testing (20%) | 5: Deployment (10%) | Total | IBM-standard effort (FTE-months) to migrate one app of each type through all 5 phases. Phase split: Discovery 15%, Design 10%, Development 45%, Testing 20%, Deployment 10%.
Simple Web App / API Service | 0.135 | 0.09 | 0.405 | 0.18 | 0.09
Mainframe / Legacy System | 0.6 | 0.4 | 1.8 | 0.8 | 0.4
ERP / Packaged Application | 0.45 | 0.3 | 1.35 | 0.6 | 0.3
Mobile Application | 0.15 | 0.1 | 0.45 | 0.2 | 0.1
Microservice / Cloud-Native | 0.09 | 0.06 | 0.27 | 0.12 | 0.06
Monolith / Legacy Custom | 0.525 | 0.35 | 1.575 | 0.7 | 0.35
COMPLEXITY-ADJUSTED EFFORT | [6 empty] | SECTION: COMPLEXITY-ADJUSTED EFFORT
Complexity Multiplier (from INPUT) | [6 empty] | Complexity Multiplier applied to every archetype. Formula: Adjusted = Base x Multiplier All Low (1.0x): Simple Web App = 0.9 x 1.0 = 0.9 All Med (1.5x): Simple Web App = 0.9 x 1.5 = 1.35
Simple Web App / API Service (adjusted)
Mainframe / Legacy System (adjusted)
ERP / Packaged Application (adjusted)
Mobile Application (adjusted)
Microservice / Cloud-Native (adjusted)
Monolith / Legacy Custom (adjusted)
WEIGHTED AVERAGE EFFORT (feeds AMU on UNITS sheet) | [6 empty] | SECTION: WEIGHTED AVERAGE EFFORT
Archetype | App Count | % of Total | Adj Effort/App | Weighted Contribution |  |  | Combines all archetypes into single average effort, weighted by app count. Formula: Weighted Avg = SUM(each archetype's % x adjusted effort)
Simple Web App / API Service
Mainframe / Legacy System
ERP / Packaged Application
Mobile Application
Microservice / Cloud-Native
Monolith / Legacy Custom
Weighted Avg Effort per App (FTE-months)
WORKED EXAMPLE: Computing Weighted Average (with default values)
Archetype | Count | % of Total | Effort/App | Contribution |  |  | Calculation Detail
Simple Web App | 3,200 | 40.0% | 0.90 | 0.3600 |  |  | 3200/8000 = 40% x 0.90 = 0.3600
Mainframe | 800 | 10.0% | 4.00 | 0.4000 |  |  | 800/8000 = 10% x 4.00 = 0.4000
ERP / Packaged | 600 | 7.5% | 3.00 | 0.2250 |  |  | 600/8000 = 7.5% x 3.00 = 0.2250
Mobile | 400 | 5.0% | 1.00 | 0.0500 |  |  | 400/8000 = 5% x 1.00 = 0.0500
Microservice | 2,200 | 27.5% | 0.60 | 0.1650 |  |  | 2200/8000 = 27.5% x 0.60 = 0.1650
Monolith/Legacy | 800 | 10.0% | 3.50 | 0.3500 |  |  | 800/8000 = 10% x 3.50 = 0.3500
TOTAL | 8,000 | 100% |  | 1.5500 |  |  | Sum = 0.36 + 0.40 + 0.225 + 0.05 + 0.165 + 0.35 = 1.55 FTE-months/app
This 1.55 FTE-months/app feeds into UNITS sheet as AMU base effort.
On UNITS: AMU Small = 1.55 x 1.0 = 1.55 ¦ Medium = 1.55 x 2.0 = 3.10 ¦ Large = 1.55 x 4.0 = 6.20

## UNITS
IBM Cybersecurity Services — Enterprise Cost Model | [25 empty] | ROW-BY-ROW FORMULA GUIDE
Units | Federated Adoption Unit (FAU) |  |  | Network / Connectivity Migration Unit (NMU) |  |  | Application Migration Unit (AMU) |  |  | Platform/Cloud/Runtime Migration Unit (PMU) |  |  | PKI/CLM/KMS Migration Unit (CMU) |  |  | Data & Storage Migration Unit (DMU) |  |  | DevSecOps & Automation Unit (DAU) |  |  | Vendor / Third-Party Unit (VTU) |  |  | Totals | Row 2: UNIT TYPE HEADERS — 8 unit types, each with Small/Medium/Large (3 cols per unit, 24 value columns total).
Estimated Units | [25 empty] | Row 3: ESTIMATED UNITS — Pulled from INPUT sheet. Total number of units to be migrated.
| Key Activities: - Roll out central QS policies, standards, and patterns to local units - Act as first-line decision and exception handling point - Support local discovery, reporting, and risk visibility - Coordinate vendors and delivery teams within the unit - Feed local constraints and risks back to central governance Size definitions: - Small: Homogeneous tech stack, low regulatory variation - Medium: Mixed platforms, moderate regulatory requirements - Large: Diverse platforms, strong regulatory pressure |  |  | Key Activities: - Endpoint & Protocol Mapping: Identify TLS, VPN, IPsec usage - Standardization & Design: Define cipher suites, TLS versions - Implementation & Automation: Update configs, automate cert lifecycle - Migration & Stabilization: Phase changes, resolve production issues Size definitions: - Small: Single network tier, automated certificate handling - Medium: Regional infrastructure, partial automation, legacy protocols - Large: Global/legacy network, manual lifecycle, high outage risk |  |  | Key Activities: - Discovery & Planning: Identify cryptographic usage and exposure - Design & Pattern Selection: Choose approved algos, libraries - Refactor & Implementation: Replace hard-coded crypto, update configs - Test, Deploy, Stabilize: Validate functionality and integrations Size definitions: - Small: Standard libraries, minimal crypto, limited integrations - Medium: Mix of standard and embedded crypto, several dependencies - Large: Custom/hardcoded crypto in business-critical legacy code |  |  | Key Activities: - Platform Crypto Assessment: Review defaults, gaps, workloads - Baseline & Architecture Design: Define hardened crypto configs - Configuration & Integration: Update platform settings, key/certs - Rollout & Validation: Rolling updates, stabilize runtime Size definitions: - Small: Cloud-native platform, default crypto configs - Medium: Shared platform, custom crypto, partial HSM integration - Large: Hybrid/bespoke runtime, inconsistent controls, high blast radius |  |  | Key Activities: - Establish crypto-agile trust foundations (CAs, trust anchors) - Automate cert issuance, rotation, revocation across environments - Migrate to quantum-safe algorithms in PKI and KMS - Standardize key generation, storage, rotation (HSMs, KMS) - Integrate PKI/KMS with apps, platforms, networks, DevSecOps Size definitions: - Small: One PKI/KMS instance, limited consumers - Medium: 2-3 PKIs/KMS domains, shared services - Large: Enterprise-wide PKI/KMS, complex trust chains |  |  | Key Activities: - Data & Risk Assessment: Identify long-lived, sensitive datasets - Encryption Strategy Design: Define re-encryption, key lifecycle - Implementation & Re-Encryption: Apply crypto changes, migrate data - Validation & Stabilization: Confirm integrity, access, recovery Size definitions: - Small: Managed storage, built-in encryption, limited re-encryption - Medium: Shared enterprise data, regulated data, custom key handling - Large: High-volume, long-retention store, crypto changes impact availability |  |  | Key Activities: - Pipeline Crypto Mapping: Identify crypto controls and gaps in CI/CD - Policy & Control Design: Define validation rules, enforcement levels - Integration & Rollout: Embed checks into pipelines and workflows - Tuning & Enablement: Reduce noise, support developer adoption Size definitions: - Small: Single CI/CD pipeline, standard tooling - Medium: Shared pipelines, policy tuning, exception handling - Large: Federated DevOps, many pipelines, high enforcement risk |  |  | Key Activities: - Dependency Identification: Identify crypto reliance and criticality - Requirement Definition: Define PQC and crypto expectations - Vendor Engagement: Validate roadmaps and remediation plans - Tracking & Exception Handling: Monitor progress, manage residual risk Size definitions: - Small: Low-risk, replaceable vendor, minimal crypto dependency - Medium: Core vendor, partial visibility, negotiable roadmap - Large: Deeply embedded/regulated vendor, limited leverage |  |  |  | Row 4: KEY ACTIVITIES — What each unit does and how Small/Medium/Large are defined.
Unit | Per governed domains / BUs / geos |  |  | Per network / connectivity domain |  |  | Per application |  |  | Per platform / cloud / runtime |  |  | Per PKI / CLM / KMS domain |  |  | Per data & storage class |  |  | Per DevSecOps pipeline |  |  | Per vendor third-party |  |  |  | Row 5: PER-UNIT LABEL — What each unit represents (e.g., 'Per application' for AMU).
Sizing | Small | Medium | Large | Small | Medium | Large | Small | Medium | Large | Small | Medium | Large | Small | Medium | Large | Small | Medium | Large | Small | Medium | Large | Small | Medium | Large |  | Row 6: SIZING — Small, Medium, Large. Complexity within each unit type.
Unit % Split per complexity | 55% | 30% | 15% | 55% | 30% | 15% | 55% | 25% | 20% | 45% | 30% | 25% | 30% | 50% | 20% | 60% | 25% | 15% | 45% | 40% | 15% | 70% | 20% | 10% |  | Row 7: UNIT % SPLIT — Client-editable. % of units that are S/M/L. Must sum to 100%. Example: AMU 55/25/20 means 55% of 8000 apps = 4400 are 'Small'.
Unit Count | [25 empty] | Row 8: UNIT COUNT = Estimated Units x Unit % Split. Example: FAU Small = 22 x 55% = 12.1 units.
Base Effort (FTE-months) | 2 | 4 | 6 | 1 | 3 | 6 |  |  |  | 2 | 4 | 8 | 2 | 5 | 9 | 1 | 2 | 5 | 1 | 2 | 4 | 0.5 | 1.5 | 3 |  | Row 9: BASE EFFORT (FTE-months) per unit. Most units: IBM-standard value. AMU: Auto-calculated from ESTIMATE!E32 x size multiplier (1.0/2.0/4.0).
Learning Curve Factor | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | Row 10: LEARNING CURVE FACTOR — Only AMU (value <1). All others = 1.0. With 8000 apps: factor = 0.4119 (~41% of baseline cost).
Effective Effort per Unit | [25 empty] | Row 11: EFFECTIVE EFFORT = Base Effort x Learning Curve Factor.
Total Effort (FTE-months) | [25 empty] | Row 12: TOTAL EFFORT = Unit Count x Effective Effort. Example: AMU Small = 4400 x 0.638 = 2,807 FTE-months.
Blended FTE-Month Rate (USD) | [25 empty] | Row 13: BLENDED FTE-MONTH RATE from CONFIG per unit type.
Unit Labour Cost (USD) | [25 empty] | Row 14: UNIT LABOUR COST = Effective Effort x Blended Rate.
Labour Cost (USD) | [25 empty] | Row 15: LABOUR COST = Unit Count x Unit Labour Cost.
Tooling / Tech Overhead % | 0% | 0% | 0% | 10% | 10% | 10% | 15% | 15% | 15% | 8% | 8% | 8% | 20% | 20% | 20% | 12% | 12% | 12% | 0% | 0% | 0% | 5% | 5% | 5% |  | Row 16: TOOLING % — IBM-standard. Varies: 0% FAU/DAU, 8% PMU, 10% NMU, 12% DMU, 15% AMU, 20% CMU, 5% VTU.
Tooling Overhead Cost (USD) | [25 empty] | Row 17: TOOLING COST = Labour Cost x Tooling %.
Subtotal | [25 empty] | Row 18: SUBTOTAL = Labour + Tooling.
Risk Contingency % | [25 empty] | Row 19: RISK % from CONFIG. Default 20%. Covers unknowns.
Risk Contingency Cost (USD) | [25 empty] | Row 20: RISK COST = Subtotal x Risk %.
UNIT TOTALS | [25 empty] | Row 21: UNIT TOTALS = Subtotal + Risk.
Grand Total (all units) | [25 empty] | Row 23: GRAND TOTAL (col Z) = Sum of all 24 unit total cells.
Central Governance & Enablement | [25 empty] | Row 24: CG&E = Grand Total x 10%. Covers PMO, governance, training.
Maturity Adjustment | [25 empty] | Row 25: MATURITY ADJUSTMENT = Grand Total x (Multiplier - 1).
TOTAL SPEND | [25 empty] | Row 27: TOTAL SPEND = Grand Total + CG&E + Maturity.
END-TO-END WALKTHROUGH (FAU Example)
STEP 1: Get unit count from INPUT
INPUT!B22 = 22 (governed delivery units)
STEP 2: Apply size split
Small 55%: 22 x 0.55 = 12.1 units
Medium 30%: 22 x 0.30 = 6.6 units
Large 15%: 22 x 0.15 = 3.3 units
STEP 3: Base effort (IBM-standard for FAU)
Small: 2.0 FTE-months ¦ Medium: 4.0 ¦ Large: 6.0
STEP 4: Learning curve (FAU = no LC)
Factor = 1.0 (learning curve only applies to AMU)
STEP 5: Effective effort = Base x LC
Small: 2.0 x 1.0 = 2.0 ¦ Medium: 4.0 ¦ Large: 6.0
STEP 6: Total effort = Count x Effective Effort
Small: 12.1 x 2.0 = 24.2 FTE-mo
Medium: 6.6 x 4.0 = 26.4 FTE-mo
Large: 3.3 x 6.0 = 19.8 FTE-mo
STEP 7: Get blended rate from CONFIG
FAU = $14,845/mo (20%x$18,400 + 30%x$14,900 + 20%x$11,600 + 10%x$9,750 + 20%x$17,000)
STEP 8: Unit labour cost = Effective Effort x Rate
Small: 2.0 x $14,845 = $29,690
Medium: 4.0 x $14,845 = $59,380
Large: 6.0 x $14,845 = $89,070
STEP 9: Labour cost = Count x Unit Labour Cost
Small: 12.1 x $29,690 = $359,249
Medium: 6.6 x $59,380 = $391,908
Large: 3.3 x $89,070 = $293,931
Total labour: $1,045,088
STEP 10: Tooling (FAU = 0%)
All sizes: $0 (FAU is governance, no tooling)
STEP 11: Subtotal = Labour + Tooling
Total: $1,045,088 + $0 = $1,045,088
STEP 12: Risk contingency = Subtotal x 20%
$1,045,088 x 20% = $209,018
STEP 13: FAU TOTAL = Subtotal + Risk
$1,045,088 + $209,018 = $1,254,106
STEP 14: Repeat for all 8 unit types, then:
Grand Total = $183,689,377
CG&E = $183,689,377 x 10% = $18,368,938
Maturity (1.0x, effect = 0) = $0
TOTAL SPEND = $202,058,314

## TIMELINE
IBM Cybersecurity Services — Multi-Year Phasing | [8 empty] | HOW TO USE THIS SHEET
PURPOSE: Distributes total program cost across 7 years. Provides annual budgets and staffing estimates.
YEAR-BY-YEAR DISTRIBUTION (%) | [8 empty] | DATA FLOW: Receives: Unit totals from UNITS, CG&E% from CONFIG, Maturity from CONFIG Produces: Annual cost forecasts and peak FTE for SUMMARY sheet
Unit Type | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Total | SECTION: YEAR DISTRIBUTION %
FAU | 20% | 20% | 20% | 15% | 10% | 10% | 5% |  | Client-editable. For each unit type, enter % of work per year. Must sum to 100%. Default patterns: FAU (governance): 20/20/20/15/10/10/5 (starts early, sustains) AMU (applications): 5/10/20/25/25/10/5 (ramps, peaks mid-program) VTU (vendors): 5/10/15/20/25/15/10 (back-loaded)
NMU | 10% | 20% | 25% | 20% | 15% | 5% | 5%
AMU | 5% | 10% | 20% | 25% | 25% | 10% | 5%
PMU | 10% | 15% | 25% | 20% | 15% | 10% | 5%
CMU | 15% | 20% | 25% | 20% | 10% | 5% | 5%
DMU | 5% | 10% | 15% | 25% | 25% | 15% | 5%
DAU | 10% | 20% | 25% | 20% | 15% | 5% | 5%
VTU | 5% | 10% | 15% | 20% | 25% | 15% | 10%
ANNUAL COST BY UNIT TYPE (USD) | [8 empty] | SECTION: ANNUAL COST
Unit Type | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Total | Annual Cost = Unit Total x Year %. Example: AMU Year 3 = $170.9M x 20% = $34.2M
FAU
NMU
AMU
PMU
CMU
DMU
DAU
VTU
Annual Subtotal (Units) | [8 empty] | Annual Subtotal: Sum of all 8 unit types for that year.
CG&E | [8 empty] | CG&E: Annual subtotal x CG&E % from CONFIG.
Maturity Adjustment | [8 empty] | Maturity: Annual subtotal x (Multiplier - 1).
ANNUAL TOTAL | [8 empty] | ANNUAL TOTAL: Budget required for that year.
STAFFING ESTIMATE | [8 empty] | SECTION: STAFFING
Unit Type | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Total | Peak FTE = Annual FTE-months / 12. This is an average, not peak. Multiply by 1.25 for safe staffing.
Annual Effort (FTE-months)
Peak FTE (headcount estimate)
Reconciliation Check | [8 empty] | Reconciliation: Checks sum of annual totals = UNITS TOTAL SPEND. Must show 'OK'.

## SUMMARY
IBM Cybersecurity Services — Executive Summary |  |  |  | HOW TO READ THIS DASHBOARD
PURPOSE: Executive-ready summary. All values auto-calculated. Present to leadership for budget approval.
TOTAL PROGRAM COST |  |  |  | TOTAL PROGRAM COST: The fully-loaded cost including all units, CG&E, maturity, risk, and learning curve.
COST BREAKDOWN BY UNIT TYPE |  |  |  | COST BREAKDOWN BY UNIT TYPE
Unit Type | Cost (USD) | % of Subtotal |  | Each unit type's total cost and % of subtotal. AMU (Application Migration) typically dominates at 80-90%.
Federated Adoption Unit (FAU) |  |  |  | FAU: Governance coordination. Typically <1% of total.
Network / Connectivity Migration Unit (NMU) |  |  |  | NMU: Network/TLS migration. Small unless many legacy zones.
Application Migration Unit (AMU) |  |  |  | AMU: THE BIGGEST COST DRIVER. Application-level crypto for all apps.
Platform/Cloud/Runtime Migration Unit (PMU) |  |  |  | PMU: Platform-level changes. Moderate cost.
PKI/CLM/KMS Migration Unit (CMU) |  |  |  | CMU: PKI/KMS infrastructure. High tooling (HSMs).
Data & Storage Migration Unit (DMU) |  |  |  | DMU: Data re-encryption. Timeline-sensitive.
DevSecOps & Automation Unit (DAU) |  |  |  | DAU: CI/CD pipeline integration. Small cost, high impact.
Vendor / Third-Party Unit (VTU) |  |  |  | VTU: Vendor coordination. PM-heavy.
Subtotal (all units)
Central Governance & Enablement
Maturity Adjustment
TOTAL SPEND
ANNUAL COST FORECAST |  |  |  | ANNUAL COST FORECAST
Year | Annual Cost (USD) | Cumulative Cost | Peak FTE | Annual Cost: What's needed that year. Cumulative: Running total. Peak FTE: Average team size. Use for annual budget requests and resource planning.
Year 1
Year 2
Year 3
Year 4
Year 5
Year 6
Year 7
KEY ASSUMPTIONS & PARAMETERS |  |  |  | KEY ASSUMPTIONS
Total Applications |  |  |  | Critical inputs driving the estimate: Total Apps: +/-10% apps = +/-10% AMU cost Complexity: All-Low (1.0x) vs All-High (2.0x) Learning Curve: At 0.41 = 59% savings Risk: 15-25% range Maturity: Score 2.6 avg = 1.0x (no change)
Complexity Multiplier
Maturity Multiplier
Risk Contingency
CG&E %
AMU Learning Curve (blended factor)
Average Blended FTE Rate
Program Duration | 7 years
COMPLETE COST BUILD-UP: How the Total is Constructed
LAYER 1: Per-Application Effort
6 app archetypes: 0.6 to 4.0 FTE-months |  |  | Weighted average = 1.55 FTE-months/app
Complexity multiplier (all Low = 1.0x) |  |  | 1.55 x 1.0 = 1.55 FTE-months/app
LAYER 2: Learning Curve (AMU only)
8,000 apps across 5 waves: 1.5x to 0.30x |  |  | Blended factor = 0.4119
Effective effort: 1.55 x 0.4119 = 0.638 (Small) |  |  | 59% cost reduction from scale/automation
LAYER 3: Enterprise Cost Model (UNITS)
8 unit types x Small/Medium/Large sizing |  |  | Counts from INPUT, efforts from ESTIMATE/CONFIG
Labour = Count x Eff Effort x Blended Rate |  |  | $13,110/mo for AMU, varies by unit
+ Tooling overhead (0-20%) |  |  | CMU 20% (HSMs), AMU 15%
+ Risk contingency (20%) |  |  | Covers unknowns and surprises
= Unit Totals across all types |  |  | Grand Total = $183,689,377
LAYER 4: Program-Level Adjustments
+ CG&E (10% of Grand Total) |  |  | ​+ $18,368,938
+ Maturity (1.0x = $0 adjustment) |  |  | Would be +$21M at 1.15x
FINAL: TOTAL SPEND |  |  | $202,058,314
SENSITIVITY:
Complexity all Medium (1.5x): ~$303M (+50%) |  |  | Doubling complexity nearly doubles cost
No learning curve (all 1.0x): ~$440M (+118%) |  |  | Scale economies are the biggest factor
10,000 apps instead of 8,000: ~$240M (+19%) |  |  | Mostly linear in app count
Maturity avg = 2.0 (1.15x): ~$223M (+10%) |  |  | Immature orgs pay more